## Start Here
Pareeksa — Team Testing Pack
A step-by-step test log. No technical knowledge needed — do each row, then record what happened.
The app: | https://pareeksa.pages.dev
The guide: | https://pareeksa-guide.pages.dev
STEP 1 — Send Adnan 5 to 7 email addresses
Different people play different roles so we can test the whole exam end to end. Send these to Adnan — he switches the accounts on; you just sign in.
How many - Role | What they do · what kind of email
1 - Exam Controller (Admin) | Runs setup: builds the exam, uploads papers, allocates markers, publishes results. -> GOOGLE account.
1 - Moderator | Settles disagreements between two markers - blind to the student's identity. -> GOOGLE account.
3 to 5 - Markers (Teachers) | Read & score scripts. Need at least 2 so two can mark one script and the moderator can resolve a clash. -> ANY email.
0 to 1 - Sub-admin (optional) | Helper with limited access (only sections you allow). -> Any email.
STEP 2 — Sign in
1. Open https://pareeksa.pages.dev in Chrome, Edge, or Safari (laptop, or tablet for marking).
2. Admin / Moderator -> 'Continue with Google'. Marker -> type your email, open the link we send you.
3. You land on your home screen. Refused? Your account isn't on yet - tell Adnan your email + role.
STEP 3 - Work down the 'Test Checklist' tab
It is split by area. Do the rows for YOUR role (others cover the rest). For each row: do the action, check what you see, set Result from the dropdown, put your name in 'Tested by', and add a note. Log EVERY step - even the ones that work.
Hit a problem? Also add it to the 'Report a Bug' tab. Nothing is too small.

## Test Checklist
# | Section | What to do (step by step) | What you should see | Result | Tested by | Notes / what happened
EVERYONE - Sign in
1 | Open the app | Go to https://pareeksa.pages.dev in Chrome/Edge/Safari. | Sign-in screen with the Pareeksa pen logo appears.
2 | Sign in - Admin/Moderator | Click 'Continue with Google' and pick your account. | You land on your home screen, no error.
3 | Sign in - Marker | Type your email, submit, open the link in the email we send. | You land on the 'My marking' dashboard.
4 | Refused sign-in | If you get a forbidden / not-allowed message, stop and note it. | Means your account isn't switched on yet - tell Adnan.
5 | Log out & back in | Click 'Log out' (top right), then sign in again. | Returns to sign-in cleanly; signing back in works.
ADMIN - Import student master data
6 | Open Master data | Click 'Master data' in the left menu. | The import page opens.
7 | Upload a list | Choose a student list file (.csv or .xlsx). | File uploads; a column-mapping preview appears.
8 | Check auto-mapping | Look at the suggested column matches (confidence chips). | Most columns are matched sensibly.
9 | Fix mappings | Correct any wrong/blank column mappings with the dropdowns. | All required fields mapped; no duplicate fields.
10 | Confirm & run | Confirm the mapping and run the import. | A summary shows created / updated / rejected counts.
11 | Rejected rows | If any rows were rejected, check the Exceptions queue. | Each rejected row shows up there as an exception.
12 | Re-import same file | Upload the exact same file again and run. | Reports 0 created / 0 updated (no duplicates).
ADMIN - Create the exam & paper
13 | New exam | Go to 'Exams' -> 'New exam'. | The 5-step setup wizard opens on step 1.
14 | Exam details | Enter name, department, session; choose marking mode + thresholds. | Fields accept your input.
15 | Create exam | Click 'Create exam'. | Advances to the Paper step.
16 | Paper details | Enter paper code, title, total marks. | Fields accept your input.
17 | Create paper | Click 'Create paper'. | Advances to the Rubric step.
ADMIN - Question paper, answer key & AI rubric
18 | Upload question paper | In the Setup-artifacts box, upload the question paper (PDF or image). | Shows a green tick with the file name.
19 | Upload answer key | Upload the answer key (PDF or image). | Shows a green tick with the file name.
20 | Propose rubric with AI | Click 'Propose rubric with AI'. | After a few seconds a note appears and the rubric fills with questions.
21 | Review the proposal | Check the proposed questions, marks, and any sub-steps. | They roughly match the real question paper.
22 | Edit the rubric | Change a label/marks; add a question or a criterion. | Edits apply; the marks total updates.
23 | Check the balance | Compare the paper total to the sum of question marks. | Shows 'balanced', or clearly flags a mismatch.
24 | Save rubric | Click 'Save rubric'. | Advances to the Ingest step.
ADMIN - Upload & ingest answer scripts
25 | Upload scripts | Upload one or more scanned answer sheets. | They upload and process; no 'Internal server error'.
26 | Ingest finishes | Wait for processing. | Advances to the Identity-region step.
27 | Identity region | Adjust the mask rectangle over the name/roll area if needed. | Preview shows the area that will be hidden from markers.
28 | Publish | Click 'Publish'. | Paper is published and ready to allocate.
ADMIN - Combined scan ingest (optional / advanced)
29 | Open Scans | Click 'Scans' in the menu. | The scans page opens.
30 | OMR template | Create or edit an OMR template using the form. | Template saves.
31 | Upload a batch | Upload a scan batch (a zip of cover + answer pages). | A batch report shows created vs excepted counts.
32 | Failed reads -> exceptions | Open the Exceptions queue. | Unreadable barcodes / low-confidence OMR / match failures appear there.
ADMIN - Allocate markers
33 | Open Allocations | Click 'Allocations'. | The paper x marker grid appears.
34 | Assign first marker | Assign a marker as 'first' on a paper. | Saves without error.
35 | Assign second marker | Assign a DIFFERENT marker as 'second'. | Saves without error.
36 | Assign moderator | Assign a moderator. | Saves without error.
37 | Duplicate guard | Try assigning the SAME person twice on one paper. | Refused with a clear message (can't be two roles).
38 | Method / caps | If shown, set allocation method/caps (manual / auto / pool). | Setting saves.
39 | Pool / auto-deal | If using a pool, confirm markers can claim, or auto-deal distributes. | Scripts get assigned to markers.
ADMIN - Approve marker enrolments
40 | Open Enrolments | Click 'Enrolments'. | The pending-enrolment queue appears.
41 | See a pending one | A marker who enrolled their face shows as 'pending'. | Their row is listed.
42 | Open it | Click the pending row. | Details open - status only, no raw video.
43 | Approve | Click 'Approve'. | Shows 'Approved' with a valid-until date; that marker can now mark.
ADMIN - Team / sub-admins (optional)
44 | Open Team | Click 'Team'. | The team page opens.
45 | Create a sub-admin | Add a sub-admin email and tick a few modules. | Sub-admin is created.
46 | Sub-admin sees only ticked | Have that sub-admin sign in. | They see ONLY the modules you ticked - nothing else.
MARKER - Enrol your face (* most important)
47 | Open enrolment | Go to the enrol screen (first marking may prompt it). | Enrolment page loads.
48 | Allow the camera | Click 'Allow' on the browser's camera prompt. | Your own live camera picture shows on screen.
49 | Capture - front | Look straight at the camera and capture. | Step advances to the next pose.
50 | Capture - left | Turn slightly left and capture. | Step advances.
51 | Capture - right | Turn slightly right and capture. | Step advances.
52 | Liveness | Complete the liveness step. | All steps done; a review screen appears.
53 | Submit enrolment | Click submit. | Success screen; your status is 'pending approval'.
MARKER - Start marking: the camera check (* most important)
54 | See your work | On the dashboard, look at your allocated batches. | Batches listed with progress counts.
55 | Claim from pool | If a pool is shown, claim a few scripts. | They appear in your queue.
56 | Start marking | Click 'Start / Resume marking' on a script. | A quick camera check runs.
57 | Recognised | Let it check your face. | It recognises YOU and the marking screen opens.
58 | Wrong-person test | Have a DIFFERENT person sit in front and try to start. | It BLOCKS them - identity-mismatch message.
59 | Self-view | While marking, find your small camera self-view. | You can see yourself in frame.
60 | Step-away lock | Move out of the camera's view for about a minute. | The session locks with a calm message.
61 | Recover | Come back into view. | It re-checks your face and unlocks; your work is intact.
MARKER - The marking tools
62 | Script loads | The scanned sheet fills the screen (fit-to-width). | Readable; nothing cut off.
63 | Page thumbnails | Use the page strip to jump between pages. | Pages switch.
64 | Zoom | Zoom in and out. | Image scales smoothly and stays sharp enough to read.
65 | Rotate a page | Use the rotate button on a sideways page. | It rotates and stays rotated.
66 | Red pen | Draw on the script with the pen tool. | Red strokes appear where you draw.
67 | Tick stamp | Place a green tick. | Tick appears on the page.
68 | Cross stamp | Place a red cross. | Cross appears on the page.
69 | 'Seen' stamp | Place the blue 'seen' stamp. | Stamp appears on the page.
70 | Text note | Add a text annotation. | A text box appears and saves.
71 | Eraser | Erase one of your marks. | It is removed.
72 | Question paper / key | Open the question-paper / answer-key links. | They open (for reference while marking).
73 | Step guidance | Look under a rubric question for the step-wise marks. | Shown as marking guidance.
MARKER - Scoring
74 | Score a question | Type a score in a question's box. | It accepts the number.
75 | Keyboard move | Use arrow keys / Enter to move between questions. | Focus jumps to the next question.
76 | Quick-marks | Use the rubric quick-mark buttons. | The score updates.
77 | Running total | Watch the running total as you score. | It updates live.
78 | 2 decimals only | Try typing a score with 3 decimal places. | It is limited/rejected to 2 decimals.
79 | Over the max | Try a score higher than the question's maximum. | It is prevented or clamped to the max.
MARKER - Save, submit & log out
80 | Autosave | After scoring, watch the save indicator. | Shows your work is saved.
81 | Reload persists | Reload the page mid-marking (don't submit). | Your scores AND pen marks are still there.
82 | Page gate | Try to submit before viewing every page. | It asks you to view all pages first.
83 | Mark pages seen | Visit each page / mark them seen. | Gate is satisfied.
84 | Submit | Click Submit. | A confirmation modal appears.
85 | Confirm | Confirm the submission. | Script shows as submitted; you return to the queue.
86 | Scan issue | On a damaged/faded scan, click 'Scan issue?' and give a reason. | Script is parked and sent to the Exceptions queue.
87 | Request unlock | After submitting, request to unlock a script. | Request goes to the admin for approval.
88 | Log out | Click 'Log out'. | Returns to sign-in; your marking stays saved.
SECOND MARKER - Blind second marking
89 | Sign in (2nd marker) | Sign in as the second marker. | Marker dashboard.
90 | Open the SAME script | Open the script the first marker already marked. | It opens for you.
91 | Blindness check | Look for the first marker's scores / pen marks. | You CANNOT see them - fields empty, total 0.
92 | Score independently | Score it yourself; give clearly different scores to test moderation. | Saves.
93 | Submit | Submit your marks. | If scores differ enough, the script goes to moderation.
MODERATOR - Resolve disagreements
94 | Sign in (moderator) | Sign in as the moderator. | You land on the moderation queue.
95 | See the queue | Find the flagged script. | It is listed in the queue.
96 | Open flagged script | Open it. | You see BOTH markers' scores and the per-question differences.
97 | Blind to identity | Look for the student's name. | No name - only an anonymous code.
98 | See guidance | Check the rubric, step pattern, and paper/key links. | All shown to help you decide.
99 | Enter final mark | Enter a fresh final score per question. | Accepts your input.
100 | Outside the range | Try a total outside both markers' totals. | Allowed - you have full judgment.
101 | Resolve | Submit the resolution. | Script becomes 'moderated'; the queue clears it.
102 | Can't reveal | Confirm a moderator can't de-anonymise / reveal names. | Not available to you (by design).
ADMIN - Exceptions & unlock requests
103 | Open Exceptions | Click 'Exceptions'. | Queue with Open / Resolved tabs appears.
104 | See open items | Look at the open exceptions. | Import rejects, scan failures, rescan reports are listed.
105 | Resolve with note | Open one, write a resolution note, click 'Fixed'. | Moves to the Resolved tab.
106 | Note is required | Try resolving with an empty note. | It won't let you - a note is required.
107 | Reject a script | On a script-linked exception, choose 'Reject script'. | Script is marked rejected (out of the exam).
108 | Unlock requests | In the unlock panel, approve a marker's unlock request. | That script becomes editable for the marker again.
ADMIN - Compile & reveal results
109 | Open Results | Click 'Results'. | The results & moderation page.
110 | Compile too early | Try Compile before everything is done. | Refused - it lists exactly what's blocking.
111 | Clear blockers | Finish marking / moderation / open exceptions. | Blockers clear.
112 | Compile | Click Compile. | Success - scripts are compiled.
113 | Reveal identities | Click 'Reveal identities'. | Student names appear (was anonymous until now).
114 | Identified export gated | Before revealing, try the identified CSV. | Refused until the reveal is done.
ADMIN - Reports & dashboards
115 | Open Reports | Click 'Reports'. | Dashboard loads.
116 | Pipeline counts | Look at scripts by stage. | Counts shown.
117 | Open work | Look at open exceptions / discrepancies / pending unlocks. | Counters shown.
118 | Throughput | Look at the marks-per-day chart. | Bars render.
119 | Speed flags | Look for markers flagged for too-fast marking. | Shown (or 'none').
120 | Leaderboard | Look at the marker leaderboard. | Markers ranked by submitted marks.
ADMIN - Export & mark sheets
121 | Anonymous CSV | Export the anonymous results CSV. | A file downloads - no student names in it.
122 | Identified CSV | After the reveal, export the identified CSV. | A file downloads - with names.
123 | Mark sheets | Open the per-student mark sheets. | One sheet per student across their papers.
124 | Print | Click Print on the mark sheets. | A clean printable layout opens.

## Report a Bug
# | Tested by | Your role | Where (screen / web address) | What you EXPECTED | What ACTUALLY happened | Screenshot? (Y/N) | How bad? 1-5
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
Tip: a screenshot saves us a lot of time. Severity: 1 = tiny annoyance, 5 = totally blocks you.